## Document Control
Item | Description
Document Title: | IT and Security Risk Register
Document ID:
Classification: | Confidential Restricted Internal Public
Version No.: | 1
Status:
Publish Date: | 2024-07-30
Revision Date:
Document Review and Approval History
(All revisions should be approved)
Version No. | Date | Reviewer(s) | Remarks
1 | 2024-07-30
Version No. | Date | Approver(s) | Remarks
1

## Overview
Risk Assessment Overview
Risk Management Process |  |  | Risk Management Process:
Risk Identification:
Identifying risk sources, areas of impacts, events, causes and possible consequences to form a comprehensive list of risks based on those events that might create, enhance, prevent, degrade, accelerate or delay the achievement of objectives.
Risk Analysis |  |  |  | Communication and Consultation | Establishing the Context | Monitoring & Review
Considering the range of causes, sources of risk, consequences and likelihood to produce a risk rating.
Risk Assessment
Risk Evaluation
Evaluate the level of risk identified during risk analysis can be ranked and prioritized according to a consistent overall ranking and rating system. |  |  |  |  | Risk Identification
Risk Treatment
Selecting one or more options for modifying risks including funding and other resource considerations |  |  |  |  | Risk Analysis
Navigation of this tool |  |  |  |  | Risk Evaluation
1 | To Identify Risks | Click Here
2 | To Analysis of Risks | Click Here
3 | To Evaluation of Risks | Click Here
4 | To Treat (Manage/Action) Risks | Click Here |  |  | Risk Treatment
5 | To Report on Risks | Click Here
6 | To View/Update Validation Rules | Click Here
Benefits of Risk Management
1 | Increasing the likelihood of achieving business objectives
2 | Encouraging proactive management of business processes
3 | Improving compliance, reporting and governance
4 | Strengthening and streamlining controls
5 | Enhancing operational effectiveness and efficiency
6 | Maximising the productive use of available resources
7 | Minimising financial loses
8 | Improving resilience and business continuity.

## Risk Assessment Register
[11 empty] | Overview | [23 empty] | Business
Strategy & Development
Human Resource & General Administration
IT and Cybersecurity Risk Assessment Register
|  |  | Risk Evaluation Criteria | [6 empty] | Risk Levels | [25 empty] | Ongoing Monitoring
|  |  | LIKELIHOOD | [6 empty] | High | 15-25 | [24 empty] | Last Reviewed
|  | 5 | Almost certain | 5 | 10 | 15 | 25 | 25 | [27 empty] | Review Frequency (# month)
|  | 4 | Very Likely | 4 | 8 | 12 | 20 | 20 |  | Medium | 5-14 | [24 empty] | Next Review Date
|  | 3 | Possible | 3 | 6 | 9 | 15 | 15 | [27 empty] | Responsibility
|  | 2 | Unlikely | 2 | 4 | 6 | 10 | 10 |  | Low | 1-4
|  | 1 | Very Unlikely | 1 | 2 | 3 | 5 | 5
|  |  |  | Minor | Medium | Serious | Major | Catastrophic
CONSEQUENCE
|  |  |  | 1 | 2 | 3 | 4 | 5 |  | 5
Risk Identification | [8 empty] | Risk Analysis | [7 empty] | Risk Treatment/ Action Plan |  |  |  | Risk Monitoring & Review | [7 empty] | before |  | after
SI No | Risk Title | Risk | Cause | Risk Category | Risk Owner | Likelihood | Impact | Inherent Risk |  | Existing Control/ Current Measure | Control Assessment | Standard Reference | Objective Evidence | Likelihood | Magnitude of Impact | Residual Risk | Risk Treatment Option | Mitigate Action/Plan | Responsibility | By When | Risk Acceptance | Risk Acceptance Approved by | Control Assessment | Remarks
#No | Enter the Title of the Risk | Enter the Identified Risk | Describe the potential causes of event occurring | Identify the relevant risk category | Identify the owner of the Risk | Assess the probability of risk event occurring | Assess the plausible impact of risk event occurring | Inherent Risk Level IR = Impact * Likelihood |  | List of existing control | Effectiveness of the Existing control |  | Objective Evidence of the treatment of the risk | Assess the probability of risk event occurring | Assess the plausible impact of risk event occurring MOI = Old Impact * Efftiveness of implemented control | Residual Risk Level | Describe the treatment to be applied to risk | Steps to treat the risk | Assign owner | Specify target resolution date | Risk Acceptance Criteria | Risk Acceptance Approved by | Effectiveness of the implemented control | Describe the Remarks if any e.g.; acceptance criteria
1 | Absence of IT Strategy | Absence of a comprehensive IT Strategy in line with business objectives may lead to unclear governance of the IT function within the company for the fulfillment of long-term and short-term goals. | Lack of cyber security strategy and roadmap | Strategic | IT Department | Very Likely | Major | High |  | Currently, IT department dosen't have any defined IT Strategy. | None |  |  | Very Likely | Major | High | Mitigate | IT department sholud develop the IT Strategy including the initiatives roadmap. | IT Department |  | No |  | None |  | 4 | 4 | 4 | 4 |  | 16 | 16
2 | The absence of periodic reviews of IT policies and procedure | The absence of periodic reviews of IT policies and procedures can result in that Policies and procedures do not reflect current practices or technologies can lead to inefficiencies and inconsistencies in IT operations. | Absence of periodic reviews of IT policies and procedures | Strategic | IT Department | Very Likely | Major | High |  | IT Policies and procedues are not reviewed priodically. IT policies and procedures were last reviewed on 10 October 2020. | None |  |  | Very Likely | Major | High | Mitigate | IT department should review and update IT Policies and Procedures periodically as per the best practices . | IT Department |  | No |  | None |  | 4 | 4 | 4 | 4 |  | 16 | 16
3 | The absence of the IT steering committee | The absence of the IT steering committee and charter may fail to provide a roadmap that defines the core vision, direction, and operations of the department. As a result, the committee may fail to support teams and operations. | The absence of the IT steering Committee and Charter | Strategic | IT Department | Very Likely | Major | High |  | IT steering committee and IT Steering committee charter has not beeen established. | None |  |  | Very Likely | Major | High | Mitigate | IT department should establish IT Steering Committee and Charter. Moreover, IT Steering Committee meeting should be held as per the frequency defined in the steering committee charter. | IT Department |  | No |  | None |  | 4 | 4 | 4 | 4 |  | 16 | 16
4 | Absence of Job Descriptions | Absence of Job Descriptions may lead employees not having a clear understanding of their roles and responsibilities within the IT Department. | The absence of Job Descriptions of the IT employees. | Strategic | IT Department | Very Likely | Serious | Medium |  | Job Descriptions are defined for the employees of the IT department. | Effective |  |  | Unlikely | Medium | Low | Mitigate | N/A | IT Department | N/A | No |  | Effective |  | 4 | 3 | 2 | 2 |  | 12 | 4
5 | Absence of Centralized IT Asset Management. | Manual asset management increases the likelihood of errors, mismanagement, and a lack of real-time visibility into the organization's asset landscape, potentially leading to operational inefficiencies and security vulnerabilities. | Absence of IT Asset Management Tool and centralized IT Asset Management. | Operational | IT Department | Possible | Major | Medium |  | The automated tool for assets discovery, tracking, and life-cycle management is not in place. | None |  |  | Possible | Major | Medium | Mitigate | IT department should implement the tool for assets discovery, tracking, and life-cycle managemen | IT Department |  | No |  | None |  | 3 | 4 | 3 | 4 |  | 12 | 12
6 | Absence of IT Asset Classification | Due to the absence of information asset classification, management may not have actual visibility of the critical assets, and risk prioritization may not be carried out. | Absence of IT Asset Classification | Operational | IT Department | Very Likely | Major | High |  | Currently, information assets are not classified by the IT department. | None |  |  | Very Likely | Major | High | Mitigate | IT department should classify all the information assets | IT Department |  | No |  | None |  | 4 | 4 | 4 | 4 |  | 16 | 16
7 | Presence of EOL and EOS IT Assets | EOS and EOL assets no longer receive security updates or patches from vendors, leaving them susceptible to known and newly discovered vulnerabilities. | Presence of EOL and EOS Assets | Operational | IT Department | Very Likely | Major | High |  | Currently, there is no record maintained for End-of-Service (EOS) and End-of-Life (EOL) statuses of assets | None |  |  | Very Likely | Major | High | Mitigate | IT department should maintain proper record of the EOS and EOL system . | IT Department |  | No |  | None |  | 4 | 4 | 4 | 4 |  | 16 | 16
8 | Absence of IT Asset Disposal | Without proper documentation of asset disposal, there is no assurance that data on disposed assets has been securely erased, potentially leading to data breaches and unauthorized access to sensitive information. | Absence of IT Asset disposal records and documenatation | Operational | IT Department | Possible | Medium | Medium |  | IT department dosen't maintain any records and documentation for there disposed off assets. | None |  |  | Possible | Medium | Medium | Mitigate | IT department should maintain propoer records and documentation of the disposed of assets. | IT Department |  | No |  | None |  | 3 | 2 | 3 | 2 |  | 6 | 6
9 | Absence of Technical Evaluation for IT Assets | Failing to perform a technical evaluation when procuring IT assets can lead to compatibility issues, performance problems, security vulnerabilities, cost overruns, operational disruptions, and project delays. | Absence of technical evaluation while procuring IT Assets. | Operational | IT Department | Possible | Medium | Medium |  | IT depatment performs the technical evaluation prior to procuring any IT Asset. | Effective |  |  | Unlikely | Minor | Low | Mitigate | NA | IT Department | NA | No |  | Effective |  | 3 | 2 | 2 | 1 |  | 6 | 2
10 | lack of an automated change management process | The lack of an automated change management system can lead to approval delays, human errors, and lack of traceability, potentially causing unauthorized changes and system downtime. | Absence of automated change management process | Operational | IT Department | Very Likely | Major | High |  | Change requests are manually raised and forwarded to the IT manager for approval. | Needs Improvement |  |  | Very Likely | Major | High | Mitigate | Implement an automated change management tool/solution to streamline the process, reduce errors, and improve traceability. | IT Department |  | No |  | Needs Improvement |  | 4 | 4 | 4 | 4 |  | 16 | 16
11 | Absence of a change testing | Absence of a change testing increases the likelihood of the undetected errors, system failures, and compromised data integrity. | Absence of change testing process. | Operational | IT Department | Very Likely | Major | High |  | Testing is conducted in a testing phase but lacks a formal documentation. | Needs Improvement |  |  | Very Likely | Serious | Medium | Mitigate | Maintain the proper documentation related to the testing of changes | IT Department |  | No |  | Needs Improvement |  | 4 | 4 | 4 | 3 |  | 16 | 12
12 | Absence of Post Implementation Review | Without a post implementation review, there is no systematic evaluation of changes post-implementation, leading to missed opportunities for improvement and unresolved issues. | Lack of Post Implementation Review process | Operational | IT Department | Very Likely | Major | High |  | IT department doesn't have any practice to perform post implementation review of the implemented changes. | None |  |  | Very Likely | Major | High | Mitigate | Perform the the review of implemented changes. | IT Department |  | No |  | None |  | 4 | 4 | 4 | 4 |  | 16 | 16
14 | Absense of Change Advisory Board | Without a Change Advisory Board (CAB), there is insufficient oversight and strategic decision-making for significant changes, leading to potential misalignments and project failures. | Absense of Change Advisory Board. | Operational | IT Department | Very Likely | Major | High |  | There is no Change Advisory Board (CAB) defined within the organization. | None |  |  | Very Likely | Major | High | Mitigate | Establish a Change Advisory Board (CAB) to oversee and approve significant changes. | IT Department |  | No |  | None |  | 4 | 4 | 4 | 4 |  | 16 | 16
15 | Prolonged Vulnerability Exposure Due to Infrequent Patching Schedule | Bi-annual patching schedule results in prolonged exposure to security vulnerabilities. | Infrequent patching process | Operational | IT Department | Very Likely | Major | High |  | The IT department patch the vulnerabilities present with in the systems Bi-Annualy. | Needs Improvement |  |  | Possible | Major | Medium | Mitigate | Increase patching frequency and ensure timely updates to minimize exposure. | IT Department |  | No |  | Needs Improvement |  | 4 | 4 | 3 | 4 |  | 16 | 12
16 | Absence of patch testing | Lack of patch testing before deploying a patch to business critical systems can lead to system instability and unexpected downtime, compromising operational efficiency. | Absence of patch testing | Operational | IT Department | Possible | Major | Medium |  | IT department have a process to test the pacthes prior to the deployement. However, there is no document available for testing of patches. | Needs Improvement |  |  | Possible | Medium | Medium | Mitigate | Maintain a propoer documentaion / reports regarding the testing of patches. | IT Department |  | No |  | Needs Improvement |  | 3 | 4 | 3 | 2 |  | 12 | 6
17 | Absence of Backup and Restoration Plan | Due to the absence of a documented Backup and Restoration Plan data not being backed up consistently or at all. This could lead to the permanent loss of critical business data in the event of a system failure, cyber-attack, or other disaster. | Absence of a documented Backup and Restoration Plan | Operational | IT Department | Very Likely | Major | High |  | IT department dosen't have any defined backup and restoration plan in place. | None |  |  | Very Likely | Major | High | Mitigate | Develop and implement a comprehensive backup and restoration plan. | IT Department |  | No |  | None |  | 4 | 4 | 4 | 4 |  | 16 | 16
18 | Absence of Backup Restoration Tetsing | Absence of backup restoration testing, there is a risk of data loss, considering data may not be restored and resumption of activities will be delayed in case of an adverse event. | Absence of Backup Restoration Tetsing Process. | Operational | IT Department | Very Likely | Major | High |  | Saudi Ceramics IT department don’t have any process or practice of backup restoration testing. | None |  |  | Very Likely | Major | High | Mitigate | Perform the backup restoration testing as per the backup restoration plan. | IT Department |  | No |  | None |  | 4 | 4 | 4 | 4 |  | 16 | 16
19 | Lack of Conducting Business Impact Analysis | Without a Business Impact Analysis (BIA), the organization may not understand the criticality of systems, leading to inadequate prioritization of recovery efforts. | Lack of Conducting Business Impact Analysis. | Operational | IT Department | Very Likely | Major | High |  | A Business Impact Analysis (BIA) has not been conducted within the organization. | None |  |  | Very Likely | Major | High | Mitigate | Conduct a Business Impact Analysis (BIA) for all services within the Saudi Ceramics. | IT Department |  | No |  | None |  | 4 | 4 | 4 | 4 |  | 16 | 16
20 | Absence of Off-Site backup | Absence of off-site backups exposes the organization to significant data loss from disasters or hardware failures, leading to operational downtime, financial losses, compliance issues, and damage to reputation. | Absence of Off-Site backups. | Operational | IT Department | Possible | Major | Medium |  | Tapes for backup are taken weekly, but these tapes are not stored off-site. | Needs Improvement |  |  | Unlikely | Major | Medium | Mitigate | Store backup tapes in a different geographical location to mitigate disaster risks. | IT Department |  | No |  | Needs Improvement |  | 3 | 4 | 2 | 4 |  | 12 | 8
21 | Absence of defined bakup retention period | Failing to define the backup retention period can lead to data loss if backups are overwritten before they are needed | Absence of defined bakup retention period. | Operational | IT Department | Possible | Medium | Medium |  | The backup retention periods for various applications are configured in the Backup Management Solution. However, these periods are not documented and approved form system owners. | Needs Improvement |  |  | Possible | Medium | Medium | Mitigate | Document and obtain approval for retention periods from system owners. | IT Department |  | No |  | Needs Improvement |  | 3 | 2 | 3 | 2 |  | 6 | 6
22 | Absense of Backup Encryption | The absence of backup encryption exposes sensitive data to unauthorized access and potential breaches. This lack of protection increases the risk of data theft, loss, or compromise, jeopardizing confidentiality and compliance. | Absense of Backup Encryption | Operational | IT Department | Very Likely | Major | High |  | The all backup data is encrypted. | Strong |  |  | Unlikely | Medium | Low | Mitigate | NA | IT Department | NA | No |  | Strong |  | 4 | 4 | 2 | 2 |  | 16 | 4
23 | Absence Root Cause Analysis (RCA) practice | Absence of a Root Cause Analysis (RCA) practice can result in unresolved recurring issues and ineffective incident management. | Absence Root Cause Analysis (RCA) practice | Operational | IT Department | Possible | Major | Medium |  | There is no practice to conduct Root Cause Analysis (RCA) of identified incidents. | None |  |  | Possible | Major | Medium | Mitigate | Perform Root Cause Analysis (RCA) of identified incidents to identify and resolve underlying issues effectively. | IT Department |  | No |  | None |  | 3 | 4 | 3 | 4 |  | 12 | 12
24 | Absence of incident repository | The absence of an incident repository for recording IT incidents within Saudi Ceramics can lead to poor incident tracking, unresolved issues, and lack of historical data for analysis. | Absence of incident repository | Operational | IT Department | Very Likely | Major | High |  | There is no incident repository for recording IT incidents within the Saudi Ceramics. | None |  |  | Very Likely | Major | High | Mitigate | Establish an incident repository to document and track all IT incidents comprehensively. | IT Department |  | No |  | None |  | 4 | 4 | 4 | 4 |  | 16 | 16
25 | Absence of incident prioritization. | Lack of criteria and practice for prioritizing and categorizing incidents based on urgency can result in delayed resolutions for critical incidents. | Absence of incident prioritization. | Operational | IT Department | Very Likely | Serious | Medium |  | There is no defined criteria and practice for prioritizing and categorizing incidents based on their urgency. | None |  |  | Very Likely | Serious | Medium | Mitigate | Develop criteria for incident prioritization and categorization to ensure timely resolution of critical incidents. | IT Department |  | No |  | None |  | 4 | 3 | 4 | 3 |  | 12 | 12
26 | Absence of access right reviews for remote users. | Periodic user access reviews for remote users are not conducted, which can lead to unauthorized access and potential security breaches. | Absence of remote periodic access reviews | Operational | IT Department | Possible | Major | Medium |  | Periodic user access reviews for VPN users are not conducted. | None |  |  | Possible | Major | Medium | Mitigate | Conduct periodic user access reviews for VPN users to ensure only authorized personnel have access. | IT Department |  | No |  | None |  | 3 | 4 | 3 | 4 |  | 12 | 12
27 | Absence of Multi-Factor Authentication (MFA) | Without Multi-factor authentication (MFA) on applications and VPN access, unauthorized individuals could easily gain entry by compromising the user accounts using brute force attack, leading to potential data breaches and compromised sensitive information. | Absence of Multi-factor authentication (MFA) for user accounts | Operational | IT Department | Very Likely | Major | High |  | Multi-Factor Authentication (MFA) is implemented in all the application of Saudi ceramics. Also, Multi-Factor Authentication (MFA) is implemented when remotely accessing SAP ERP through the VPN. | Effective |  |  | Unlikely | Minor | Low | Mitigate | NA | IT Department | NA | No |  | Effective |  | 4 | 4 | 2 | 1 |  | 16 | 2
28 | Absence of Network Monitoring | Without network monitoring, security breaches and performance issues may go undetected, leading to potential data loss and operational disruptions. This lack of visibility can also result in non-compliance and extended downtime, impacting business continuity and efficiency. | Absence of Network Monitoring | Operational | IT Department | Very Likely | Serious | Medium |  | IT department is using solar winds for the monitoring of Saudi ceramic’s network. | Effective |  |  | Unlikely | Minor | Low | Mitigate | NA | IT Department | NA | No |  | Effective |  | 4 | 3 | 2 | 1 |  | 12 | 2
29 | Absence of dedicated cybersecurity function | Without a dedicated cybersecurity function and steering committee, the organization may experience inconsistent security policies and cybersecurity measures, leading to scattered decision-making and oversight. | Lack of Cybersecurity Function and CS Steering Committee | Strategic | IT Department | Very Likely | Major | High |  | Saudi Ceramics dosen't have dedicated cybersecurity function and steering committee | None |  |  | Very Likely | Major | High | Mitigate | Establishing a dedicated cybersecurity function and steering committee enhances decision-making and oversight, thereby effectively addressing cybersecurity risks. | IT Department |  | No |  | None |  | 4 | 4 | 4 | 4 |  | 16 | 16
30 | Absence of Cybersecurity Policies and Procedures. | Due to lack of Cybersecurity policies and procedures, all the Cybersecurity related task would be performed on Ad hoc basis leading to inconsistencies and inefficiencies in performing day to day operations and required tasks. | Lack of Cybersecurity policies and procedures | Operational | IT Department | Very Likely | Major | High |  | Saudi Ceramics dosen't have cybersecurity policies and procedures. | None |  |  | Very Likely | Major | High | Mitigate | Develop the Cybersecurity policies and procedures, get it approved by the senior management and implement it. | IT Department |  | No |  | None |  | 4 | 4 | 4 | 4 |  | 16 | 16
32 | Lack of Cybersecurity in Human Resources | Failure to implement comprehensive cybersecurity requirements for human resources can lead to significant data breaches and insider threats, jeopardizing the organization's sensitive information and overall security posture | Lack of Cybersecurity in Human Resources | Operational | IT Department | Possible | Major | Medium |  | Saudi Ceramic dosen't have defined and documented cybersecurity requirements for Human Resources | None |  |  | Possible | Major | Medium | Mitigate | It is recommended to define and document cybersecurity requirements for Human Resources | IT Department |  | No |  | None |  | 3 | 4 | 3 | 4 |  | 12 | 12
33 | Lack of Cybersecurity Awareness and Training | The absence of a security training and awareness program may lead to employees being unaware of the steps to take during potential incidents, or they may become vulnerable to compromise through social engineering attacks. | Lack of Cybersecurity Awareness and Training | Operational | IT Department | Very Likely | Major | High |  | Saudi Ceramics dosen't have defined any awareness and training plan. Moreover, the awareness sessions and trainings are also not conducted. | None |  |  | Very Likely | Major | High | Mitigate | Develop awarness and training program and based on that program conduct regular security training sessions for employees to educate them on recognizing and responding to potential security incidents and best practices. | IT Department |  | No |  | None |  | 4 | 4 | 4 | 4 |  | 16 | 16
34 | Absence of Identity and Access Management Process | Inadequate identity and access management processes can lead to unauthorized access to sensitive data and systems, increasing the risk of data breaches and insider threats. | Inadequate Identity and Access Management Process | Operational | IT Department | Possible | Major | Medium |  | Saudi Ceramics has implemented strong password policies. Also, reviews of access rights are performed on a periodic bases. | Effective |  |  | Unlikely | Minor | Low | Mitigate | N/A | IT Department | N/A | No |  | Effective |  | 3 | 4 | 2 | 1 |  | 12 | 2
35 | Inadequate Management of Malware and Virus Protection | Failure to implement up-to-date malware protection measures can leaves server and workstations vulnerable to infections, potentially leading to data breaches, system disruptions, and loss of sensitive information. | Inadequate Management of Malware and Virus Protection on Servers and Workstations | Operational | IT Department | Very Likely | Major | High |  | Saudi Ceramics is using Trellix Anti-Virus solution for the advanced, up-to-date and secure management of malware and Virus protection on servers and workstations. | Effective |  |  | Unlikely | Medium | Low | Mitigate | N/A | IT Department | N/A | No |  | Effective |  | 4 | 4 | 2 | 2 |  | 16 | 4
36 | Absence of Centralized Clock Synchronization | Without centralized clock synchronization, timestamps across systems may differ, leading to inconsistencies in logging, auditing, and transaction records. | Absence of Centralized Clock Synchronization | Operational | IT Department | Unlikely | Serious | Medium |  | Centralized Clock synchronization is done by NTP server | Effective |  |  | Very Unlikely | Minor | Low | Mitigate | N/A | IT Department | N/A | No |  | Effective |  | 2 | 3 | 1 | 1 |  | 6 | 1
37 | Lack of Email Security | Due to the absence of cybersecurity measures, email services are vulnerable to phishing and social engineering attacks, potentially leading to unauthorized access and data breaches. | Lack of Email Security | Operational | IT Department | Very Likely | Major | High |  | Cybersecurity measure regarding the email security are in place. | Effective |  |  | Unlikely | Minor | Low | Mitigate | N/A | IT Department | N/A | No |  | Effective |  | 4 | 4 | 2 | 1 |  | 16 | 2
38 | Inadequate Network Security | Inadequate network security measures may lead to unauthorized access to sensitive data, resulting in data loss or theft that can damage the organization's reputation and lead to financial losses. | Inadequate Network Security | Operational | IT Department | Very Likely | Major | High |  | Cybersecurity measure regarding the network security are in place. Also, Saudi Ceramic is using NAC solution for the Management and restrictions on network services, protocols and ports. | Effective |  |  | Unlikely | Medium | Low | Mitigate | N/A | IT Department | N/A | No |  | Effective |  | 4 | 4 | 2 | 2 |  | 16 | 4
39 | Absence of Encryption | Due to the absence of encryption, sensitive data transmitted over networks or stored on devices may become vulnerable to interception and unauthorized access, leading to data breaches and privacy violations. | Absence of Encryption | Operational | IT Department | Very Likely | Major | High |  | Saudi Ceramics doesn't have any defined cryptographic solutions standards. Moreover, data at rest in server, databases, etc is also not encrypted. | None |  |  | Very Likely | Major | High | Mitigate | Define the cryptographic standards, get it approved by the senior management and implement it. | IT Department |  | No |  | None |  | 4 | 4 | 4 | 4 |  | 16 | 16
40 | Absence of Vulnerability Management | Without an effective vulnerability management process, unpatched vulnerabilities can remain undetected, leaving systems exposed to cyber attacks potentially causing financial and reputational damage. | Inadequate Vulnerability Management Process | Operational | IT Department | Possible | Major | Medium |  | Saudi Ceramics has performed vulnerability assessment on the Q2 2024.However, Saudi Ceramics dosen't have any policy and process defined for the vulnerability management. | Needs Improvement |  |  | Possible | Major | Medium | Mitigate | Define the vulnerability management policy and procedure, get it approved by the senior management and implement it. | IT Department |  | No |  | Needs Improvement |  | 3 | 4 | 3 | 4 |  | 12 | 12
41 | Absence of penetration testing | Due to the absence of penetration testing, critical security flaws and vulnerabilities may go unnoticed, leaving the organization exposed to potential cyber attacks and data breaches. | Lack of Penetration Testing | Operational | IT Department | Possible | Major | Medium |  | Saudi ceramic has performed penetration testing for Internet-facing services and its technical components on the Q2 2024.However, Saudi Ceramics dosen't have any policy and process defined for the Penetration testing. | Needs Improvement |  |  | Possible | Major | Medium | Mitigate | Define the penetration testing policy and procedure, get it approved by the senior management and implement it. | IT Department |  | No |  | Needs Improvement |  | 3 | 4 | 3 | 4 |  | 12 | 12
42 | Absence of Security Information and Event Management (SIEM) solution | The absence of SIEM solution may hinders the ability to correlate and analyze security events, making it difficult to effectively respond and mitigate security incidents. | Absence of Security Information and Event Management (SIEM) | Operational | IT Department | Very Likely | Major | High |  | Saudi Ceramics doesn't have any Security Information and Event Management (SIEM) | None |  |  | Very Likely | Major | High | Mitigate | Deploy a SIEM solution to centrally manage and analyze security event data from various sources, enabling real-time threat detection and incident response. | IT Department |  | No |  | None |  | 4 | 4 | 4 | 4 |  | 16 | 16
43 | Lack of cybersecurity incident management | Lack of cybersecurity incident management process may result in delays in detecting, responding to, and mitigating security incidents, resulting in prolonged exposure and increased damage. | Absence of Incident Management Process | Operational | IT Department | Very Likely | Major | High |  | Saudi Ceramics doesn't have any defined and documented Cybersecurity Incident Management. | None |  |  | Very Likely | Major | High | Mitigate | Develop and implement incident management process that includes detection, response, recovery, and reporting procedures to ensure effective handling of security incidents. | IT Department |  | No |  | None |  | 4 | 4 | 4 | 4 |  | 16 | 16
44 | Absence of a threat management | The absence of a threat management process can lead to inefficient allocation of resources, as the organization may not identify, assess, prioritize, and mitigate threats appropriately. | Lack of Threat Management Process | Operational | IT Department | Very Likely | Major | High |  | Saudi Ceramics doesn't have any defined and documented Cybersecurity Threat Management process. | None |  |  | Very Likely | Major | High | Mitigate | Develop and deploy a threat management process that includes threat identification, assessment, prioritization, and mitigation strategies to protect against potential threats. | IT Department |  | No |  | None |  | 4 | 4 | 4 | 4 |  | 16 | 16
45 | Absence of Secure Asset Disposal | Failure to properly dispose of and destroy assets containing sensitive information may result in data retrieval and exploitation, leading to data breaches and privacy violations. | Inadequate Secure Asset Disposal and Destruction | Operational | IT Department | Possible | Medium | Medium |  | Saudi Cermaics dosen't have any parctice to securely dispose of information assets. | None |  |  | Possible | Medium | Medium | Mitigate | Develop and enforce policies for the secure disposal and destruction of assets, ensuring that all sensitive data is irretrievably removed before disposal. | IT Department |  | No |  | None |  | 3 | 2 | 3 | 2 |  | 6 | 6
46 | Absence of Web Application Firewall (WAF) | Due to the absence of WAF, web applications are more susceptible to common threats such as SQL injection, cross-site scripting (XSS), potentially resulting in unauthorized access to sensitive data and subsequent data breaches. | Absence of Web Application Firewall (WAF) | Operational | IT Department | Possible | Major | Medium |  | Web Application firewall is not implemented to secure the web applications of Saudi Ceramics. | None |  |  | Possible | Major | Medium | Mitigate | Implement WAF to monitor and filter traffic between web applications and the internet, protecting against common web-based threats and vulnerabilities. | IT Department |  | No |  | None |  | 3 | 4 | 3 | 4 |  | 12 | 12
47 | Lack of Physical and Virtual Segmentation of OT/ICS | The absence of segmentation while connecting industrial networks directly to external networks (such as the internet, wireless, or remote access) significantly increases the attack surface, making critical systems more vulnerable to cyber attacks. | Lack of Physical and Virtual Segmentation | Operational | IT Department | Very Likely | Major | High |  | Physical and virtual segmentation is there when connecting systems and industrial networks with external networks (e.g., Internet, wireless, remote access). | Effective |  |  | Unlikely | Minor | Low | Mitigate | NA | IT Department | NA | No |  | Effective |  | 4 | 4 | 2 | 1 |  | 16 | 2
48 | Absence of Data Classification | Without data classification, identifying sensitive data that requires protection becomes challenging, thereby increasing the risk of data breaches and cyber attacks. | Absence of data classification | Operational | IT Department | Very Likely | Major | High |  | Data classification and labelling is not performed to secure the confidential data. | None |  |  | Very Likely | Major | High | Mitigate | It is recommended to define and implement a comprehensive data classification framework to categorize data based on its sensitivity and importance. | IT Department |  | No |  | None |  | 4 | 4 | 4 | 4 |  | 16 | 16
49 | Absence of SLAs and NDAs with Third-Party Vendors | Without Service Level Agreements (SLAs), there is no clear understanding of service expectations, performance standards, or remedies for non-compliance, leading to potential service disruptions and unmet business needs. | Absence of SLAs and NDAs with Third-Party Vendors | Operational | IT Department | Very Likely | Major | High |  | SLAs and NDAs are defined with third-party vendors. | Effective |  |  | Very Unlikely | Medium | Low | Mitigate | NA | IT Department | NA | No |  | Effective |  | 4 | 4 | 1 | 2 |  | 16 | 2
[32 empty] | Total | 650 | 503
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Write full form
Note on D48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Full form
Note on E48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Full form
Note on D52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change it, not relevant

## Sheet1 (hidden)
Catastrophic
Major
Serious
Medium
Minor

## Validations
Overview
Risk Category | Likelihood
Startegic | The probability of risk occurring, say within the next twelve months, that can be expressed in terms of a percentage between 0% and 100%
Financial | RATING | POTENTIAL FOR RISK TO OCCUR | PROBABILITY
Operational | Almost Certain | Likely to occur frequently | 75%-100%
Compliance | Very Likely | Likely to occur several times a year | 50%-75%
| Possible | Possibly occurs once a year | 10%-50%
| Unlikely | Likely to occur once every few years | 5%-10%
| Very Unlikely | May occur once in 2-3 years | 1-5%
Impact
The potential outcome of a risk event that affects a firm's business objectives on the assumption that an event has occurred and the most probable consequence has resulted rather than the worst-case scenario.
| RATING | POTENTIAL FOR RISK TO OCCUR
| Catastrophic | Impact to the asset is high and the consequence of impact is disastrous
| Major | Impact to the asset and its’ consequence is high
| Serious | Impact to the asset and its consequence is moderate
| Medium | Impact would be minor, manageable within Saudi Ceramics
| Minor | The consequences would have insignificant impact
Level of Risk
The ranking assigned after considering the likelihood and consequence of a risk
| Risk Level | Activity | Range
| High | Needs Action | 15-25
| Medium | Needs Attention / Improvement | 5-14
| Low | No Attention needed | 1-4
Control Assessment
Any action or activity that the firm has in place that either reduces the likelihood of a risk event occurring or minimizes the potential for impact arising from that event.
| RATING | ACTION | DESCRIPTION
| Effective | Effective | Controls and/or management activities are properly designed and operating as intended.
| Strong | Limited improvement opportunity | Controls and/or management activities are properly designed and operating, with limited opportunities for improvement identified.
| Moderate | Moderate improvement opportunity | Controls and/or management activities are in place, with opportunities for improvement identified.
| Needs Improvement | Significant improvement opportunity | Limited controls and/or management activities are in place, high level of risk remains.
| None | Critical improvement opportunity | Controls and/or management activities are non-existent or have major deficiencies and don't operate as intended.
Risk Treatment Option
Depending on the type and nature of the risk, the following options are available:
| Option | Treatment
| Avoid | Deciding not to proceed with the activity that introduced the unacceptable risk, choosing an alternative more acceptable activity that meets business objectives, or choosing an alternative less risky approach or process.
| Mitigate | Implementing a strategy that is designed to reduce the likelihood or consequence of the risk to an acceptable level, where elimination is considered to be excessive in terms of time or expense.
| Share/ Transfer | Implementing a strategy that shares or transfers the risk to another party or parties, such as outsourcing the management of physical assets, developing contracts with service providers or insuring against the risk. The third-party accepting the risk should be aware of and agree to accept this obligation.
| Accept | Making an informed decision that the risk rating is at an acceptable level or that the cost of the treatment outweighs the benefit. This option may also be relevant in situations where a residual risk remains after other treatment options have been put in place. No further action is taken to treat the risk, however, ongoing monitoring is recommended.

## Report
Overview
Risk Report
Before Mitigation of the Risk
Risk Levels Types | Risk Levels in Nos | Percentage |  | Potential Risk Value
650
High | 29 | 61.7%
Medium | 18 | 38.3% |  | Residual Risk Value
Low | 0 | 0% |  | 503
Total | 47 | 100%
Percentage of Risk Reduction
77.38%
|  |  |  | Total No.of Risks Accepted | 0
After Mitigation of the Risk |  |  |  | Total No.of Risks not Accepted | 47
Risk Levels Types | Risk Levels in Nos | Percentage
High | 20 | 42.55%
Medium | 15 | 31.91%
Low | 12 | 25.53%
Total | 47 | 100%