## Table 1
💻 🔐 100 Digital Risks That Threaten Modern Enterprises – Stay Smart, Stay Safe
Risk ID | Risk Title | Type of Risk | Description | Risk Rating | Likelihood (1–5) | Impact (1–5) | Mitigating Actions | Risk Owner | Status
DR1 | System Downtime | IT Infrastructure | Unplanned outages of critical systems halt operations. | High | 4 | 5 | Redundant servers, backup systems, 24/7 monitoring | IT Operations Manager | Open
DR2 | Cybersecurity Breach | Cyber Risk | Unauthorized access to sensitive systems and data. | High | 4 | 5 | Firewalls, encryption, regular security audits, training | CISO | Open
DR3 | Ransomware Attack | Cyber Threat | Malicious software locks access to data or systems. | High | 3 | 5 | Endpoint protection, regular backups, response plans | IT Security Lead | Open
DR4 | Legacy System Failure | IT Obsolescenc e | Outdated systems crash or do not integrate with new tools. | Medium | 3 | 4 | System modernization roadmap, legacy risk register | IT Strategy Head | Open
DR5 | Data Privacy Violation | Regulatory Compliance | Breach of GDPR or data protection laws due to mishandling of PII. | High | 3 | 5 | Data governance policies, anonymization, compliance audits | Data Protection Officer | Open
DR6 | Cloud Service Disruption | Third-Party Risk | Downtime or issues in external cloud platforms halt services. | High | 4 | 4 | Multi-cloud strategy, SLA reviews, failover systems | Cloud Manager | Open
DR7 | Unauthorized Access | Identity Management | Weak access controls enable internal or external breaches. | High | 3 | 5 | Multi-factor authentication, RBAC, user access reviews | IT Security Lead | Open
DR8 | Inadequate Cyber Awareness | Human Factor | Staff untrained on cybersecurity pose phishing/social engineering risk. | Medium | 4 | 4 | Security awareness programs, mock phishing tests | HR & IT Security | Open
DR9 | Incomplete System Integration | Digital Transformati on | Fragmented systems cause data silos, duplication, and delays. | Medium | 3 | 4 | Use of APIs, integration testing, ERP alignment | Digital Transformation Lead | Open
DR10 | Third-Party Software Vulnerabilities | Vendor Risk | Bugs in vendor tools expose the enterprise to cyber threats. | High | 3 | 4 | Software vetting, patch management, contractual clauses | Procurement & IT | Open
DR11 | Poor Data Quality | Data Governance | Inaccurate or inconsistent data undermines decisions and automation. | Medium | 3 | 4 | Data validation rules, master data governance, audits | Data Governance Lead | Open
DR12 | AI/ML Bias or Misuse | Emerging Tech Risk | Unchecked AI algorithms produce discriminatory or flawed outcomes. | Medium | 2 | 5 | AI ethics review, algorithm validation, governance board | AI Product Owner | Open
DR13 | Inadequate IT Budgeting | Strategic & Financial | Underfunded IT roadmap delays transformation and increases risk exposure. | Medium | 3 | 4 | Multi-year IT planning, ROI evaluation, stakeholder buy-in | CIO | Open
DR14 | Shadow IT | Operational | Unapproved tools or systems used without IT oversight create hidden risks. | Medium | 4 | 4 | IT policy enforcement, software inventory audits, training | IT Governance | Open
DR15 | Phishing Attacks | Cyber Risk | Deceptive emails targeting staff to steal credentials or data. | High | 4 | 4 | Anti-phishing tools, email filters, user training campaigns | CISO | Open
DR16 | Insider Threats | Cyber Risk | Malicious or negligent actions by internal employees compromise security. | High | 3 | 5 | Access controls, activity monitoring, whistleblower systems | CISO | Open
DR17 | Ineffective Change Management | Operational | Poorly managed system updates lead to errors or disruptions. | Medium | 3 | 4 | Change control board, rollback plans, user testing | IT Change Manager | Open
DR18 | API Security Risks | Integration & DevOps | Exposed or unprotected APIs create backdoor vulnerabilities. | High | 3 | 5 | API gateway security, rate limiting, authentication protocols | DevSecOps | Open
DR19 | IoT Device Exploits | Technology Risk | Connected devices can be entry points for cyberattacks. | Medium | 3 | 4 | Network segmentation, firmware updates, secure configurations | IoT Security Lead | Open
DR20 | Inadequate Backup & Recovery | Business Continuity | Incomplete backups or long recovery times cause prolonged outages. | High | 3 | 5 | Disaster recovery testing, backup automation, cloud recovery | IT Infrastructure | Open
DR21 | Lack of Digital Literacy | Workforce Capability | Staff unable to use or adapt to digital tools reduces efficiency and creates risk. | Medium | 4 | 3 | Digital training programs, onboarding guides, tech champions | L&D Team | Open
DR22 | Mobile Device Vulnerabilities | Endpoint Security | Weakly secured mobile phones and tablets become threat vectors. | Medium | 3 | 4 | MDM tools, remote wipe capability, device usage policies | IT Security Team | Open
DR23 | AI Explainability Failure | Ethical AI | Complex models that can’t be interpreted lead to trust and compliance issues. | Medium | 2 | 5 | Model transparency protocols, explainable AI tools | AI Governance Lead | Open
DR24 | Denial-of- Service (DoS) Attacks | Cyber Threat | Systems are intentionally overwhelmed, disrupting access and operations. | High | 3 | 5 | DoS protection, bandwidth throttling, firewall rules | Network Admin | Open
DR25 | Software License Violations | Legal & Compliance | Use of unlicensed or expired software may result in legal penalties. | Medium | 3 | 4 | Software asset management, vendor audits, legal checks | IT Compliance | Open
DR26 | Inadequate Digital Roadmap | Strategic Planning | Lack of a clear digital vision delays innovation and increases redundancy. | Medium | 2 | 5 | Develop digital strategy, stakeholder alignment, reviews | CIO | Open
DR27 | Cloud Cost Overruns | Financial | Unmonitored consumption of cloud services causes budget overspending. | Medium | 3 | 4 | Cost control policies, usage dashboards, cloud financial ops (FinOps) | Cloud Architect | Open
DR28 | Poor User Experience (UX) | Product & Innovation | Bad interfaces or laggy systems reduce engagement and increase errors. | Medium | 3 | 3 | Usability testing, feedback loops, continuous UI improvement | Product Manager | Open
DR29 | Software Patch Delays | IT Operations | Failure to apply updates leads to known vulnerabilities remaining unpatched. | High | 3 | 5 | Patch management schedules, vulnerability scanning | IT Ops Lead | Open
DR30 | AI Model Drift | AI & Analytics | Degraded AI performance over time due to changes in data patterns. | Medium | 2 | 5 | Model monitoring, regular retraining, performance metrics | Data Science Lead | Open
DR31 | Misconfigured Cloud Settings | Cloud Security | Incorrect configurations expose sensitive data or services to public access. | High | 4 | 5 | Cloud security reviews, auto- scanning tools, team training | Cloud Security Engineer | Open
DR32 | Weak Vendor SLA Enforcement | Third-Party Management | Service providers failing SLA terms affect uptime or performance. | Medium | 3 | 4 | Regular reviews, penalty clauses, SLA dashboards | Procurement & IT | Open
DR33 | Digital Project Overruns | Project Risk | Poor scope, time, or budget control leads to delays and cost blowouts. | Medium | 3 | 4 | Agile practices, PM dashboards, milestone reviews | Digital PMO | Open
DR34 | IT & Business Misalignment | Strategic Alignment | Lack of coordination between IT and business goals leads to wasted resources. | Medium | 3 | 4 | Joint planning sessions, IT- business liaisons | CIO / Business Heads | Open
DR35 | Shadow AI Initiatives | Innovation Governance | Unofficial AI projects running without oversight create compliance issues. | Medium | 3 | 4 | AI use policy, project registry, risk reviews | AI Program Office | Open
DR36 | Data Loss via Remote Work | Operational | Laptops or mobile access without controls lead to data leakage. | Medium | 4 | 4 | Endpoint protection, secure VPNs, user training | IT Security Lead | Open
DR37 | Social Engineering Attacks | Cybersecurit y | Exploitation of human psychology to manipulate employees into breaching security. | High | 3 | 5 | Security drills, awareness campaigns, escalation SOPs | CISO | Open
DR38 | Inadequate Digital KPIs | Performance Risk | Absence of digital metrics limits performance monitoring and optimization. | Medium | 3 | 4 | Define KPIs, dashboards, digital analytics reviews | Digital Strategy Lead | Open
DR39 | Poor Software Testing Practices | Quality Assurance | Bugs slip into production due to weak or skipped testing phases. | High | 3 | 4 | Automated testing, QA standards, test coverage metrics | QA Lead | Open
DR40 | Data Migration Failures | Transformati on Risk | Data loss or corruption occurs during cloud/system migrations. | High | 3 | 5 | Data validation, test runs, rollback procedures | Migration Lead | Open
DR41 | BYOD (Bring Your Own Device) Risks | Device Management | Personal devices used for work without controls increase exposure. | Medium | 4 | 3 | BYOD policy, containerization, endpoint protection | IT Governance | Open
DR42 | Dark Web Data Exposure | External Threat | Leaked credentials or data circulating on dark web increases breach risk. | Medium | 2 | 5 | Dark web monitoring tools, password resets, incident alerts | SOC Team | Open
DR43 | Delayed Vulnerability Remediation | IT Risk | Known vulnerabilities remain unpatched beyond acceptable timelines. | High | 3 | 5 | Vulnerability management system, SLA tracking | IT Security Team | Open
DR44 | Inadequate Role-Based Access Control (RBAC) | Access Control | Over-privileged users create unnecessary access risk. | Medium | 3 | 4 | RBAC policy enforcement, least privilege principle | IT Admin | Open
DR45 | Lack of Disaster Recovery Drills | Business Continuity | Teams are unprepared for major disruptions due to untested recovery plans. | High | 3 | 5 | Periodic simulations, BCP/DR testing calendar | BCM Coordinator | Open
DR46 | Lack of Real- Time Monitoring | Infrastructure & Ops | Inability to detect issues promptly causes delays in response and recovery. | High | 3 | 5 | Implement SIEM, log management, automated alerts | IT Ops Lead | Open
DR47 | Inadequate Incident Response Plan | Cybersecurit y | Lack of structured response process worsens the impact of breaches. | High | 3 | 5 | Develop IR plan, tabletop exercises, escalation workflow | CISO | Open
DR48 | Over- Dependency on Single Tech Vendor | Strategic | Heavy reliance on one vendor limits flexibility and increases vendor risk. | Medium | 3 | 4 | Diversify vendors, review exit strategies, periodic risk reviews | Procurement | Open
DR49 | AI Ethics Violations | Governance & Compliance | AI systems making decisions without ethical oversight may cause reputational harm. | Medium | 2 | 5 | Establish AI ethics committee, bias audits, fairness KPIs | AI Program Manager | Open
DR50 | SaaS Subscription Sprawl | Financial & Operational | Proliferation of unused or redundant SaaS tools leads to cost inefficiency and risk. | Medium | 4 | 3 | SaaS inventory tracking, usage audits, central procurement policy | IT Finance Controller | Open
DR51 | Poor Data Retention Practices | Compliance | Failure to follow retention schedules may result in regulatory penalties or data loss. | Medium | 3 | 4 | Retention policy, archive strategy, automated clean-up | Data Governance | Open
DR52 | AI Hallucinations or Inaccurate Outputs | AI & Analytics | Generative AI tools provide false information that leads to bad decisions. | Medium | 2 | 5 | Human-in-the-loop reviews, source verification, prompt controls | AI Application Owner | Open
DR53 | Insufficient Encryption Standards | Information Security | Weak or missing encryption protocols expose sensitive data to theft. | High | 3 | 5 | End-to-end encryption, encryption audits, key management systems | InfoSec Lead | Open
DR54 | Lack of Interoperability | Technology Integration | Systems unable to communicate effectively, creating delays and inefficiencies. | Medium | 3 | 4 | Middleware solutions, open standards, integration architecture | Enterprise Architect | Open
DR55 | Delayed Threat Intelligence Response | Cyber Risk | Slow adaptation to new threat intel results in increased exposure. | High | 3 | 4 | Subscribe to threat intel feeds, automate rule updates | Security Operations Center | Open
DR56 | Uncontrolled Open-Source Usage | Development | Open-source components used without vetting may contain vulnerabilities. | Medium | 3 | 4 | SBOM (Software Bill of Materials), vulnerability scanning | DevSecOps | Open
DR57 | Ineffective Privileged Access Management | Identity & Access | Admin-level accounts are not properly tracked or restricted. | High | 3 | 5 | PAM tools, vaulting, session logging, access reviews | IAM Lead | Open
DR58 | Inefficient Ticketing & ITSM Processes | Service Management | Delayed issue resolution due to poor service workflows and bottlenecks. | Medium | 3 | 3 | ITSM tool optimization, KPI tracking, SLA management | Service Desk Manager | Open
DR59 | Misuse of Collaboration Platforms | Digital Workplace | Sensitive data shared carelessly across chat or file- sharing apps. | Medium | 3 | 3 | User training, access permissions, data classification policy | IT Governance | Open
DR60 | AI Regulation Non-Compliance | Regulatory Risk | Use of AI systems not aligned with new AI governance laws (e.g., EU AI Act). | Medium | 2 | 5 | Legal review, AI compliance checklist, documentation of AI models | Compliance Officer | Open
DR61 | Data Sovereignty Violation | Compliance & Legal | Data stored or processed outside jurisdictional boundaries, violating regional laws. | High | 3 | 5 | Geo-restriction policies, regional data centers, legal oversight | Data Privacy Officer | Open
DR62 | Poor API Governance | Integration & Security | Untracked, unmanaged APIs introduce vulnerabilities and data exposure. | Medium | 3 | 4 | API catalog, API gateway controls, documentation standards | API Manager | Open
DR63 | Lack of DevSecOps Integration | Software Development | Security is not integrated into the development lifecycle, causing vulnerabilities. | Medium | 3 | 4 | Secure SDLC, integrated scanning tools, DevSecOps policy | DevOps Lead | Open
DR64 | AI Drift in Production | AI & Analytics | AI models become inaccurate due to environmental changes or data evolution. | Medium | 2 | 5 | Continuous monitoring, model retraining, drift alerts | AI Operations Lead | Open
DR65 | Inadequate Mobile App Security | Cybersecurit y | Mobile applications vulnerable to injection, MITM attacks, or unauthorized access. | High | 3 | 5 | Code obfuscation, secure coding practices, security testing | App Security Engineer | Open
DR66 | Lack of Digital Innovation Pipeline | Strategic | No structured innovation funnel for testing or scaling digital ideas. | Medium | 2 | 4 | Innovation lab, PoC process, cross-functional idea management | Digital Innovation Lead | Open
DR67 | Unclear Ownership of Digital Assets | Governance | Ambiguity in asset responsibilities causes oversight or duplication. | Medium | 3 | 3 | Digital asset registry, RACI charts, governance council | Digital Asset Manager | Open
DR68 | Insecure Dev/Test Environments | Development & Security | Non-production environments lack security, leading to backdoor threats. | Medium | 3 | 4 | Environment segregation, access controls, encryption | DevSecOps | Open
DR69 | Incomplete Security Logging | Cybersecurit y | Lack of visibility due to poor or inconsistent security logging practices. | High | 3 | 5 | Centralized logging (SIEM), log retention policy, alerting | Security Operations | Open
DR70 | Absence of Digital Skills Benchmarking | Workforce | Skills not assessed regularly, leading to digital capability gaps. | Medium | 3 | 3 | Skill assessments, digital maturity tools, L&D programs | HR & IT | Open
DR71 | Overlooked Bot Traffic | Digital Operations | Bots skew analytics, consume resources, or simulate attacks. | Medium | 3 | 3 | Bot filters, CAPTCHA, behavioral detection | Web Security Analyst | Open
DR72 | Intellectual Property Theft | Legal & Security | Loss or theft of proprietary code, designs, or trade secrets. | High | 3 | 5 | NDAs, DLP tools, access control, legal escalation process | IP Compliance Officer | Open
DR73 | Tech Debt Accumulation | Engineering | Unaddressed shortcuts in code or architecture limit scalability and performance. | Medium | 4 | 3 | Refactoring cycles, technical debt KPIs, engineering sprints | Engineering Manager | Open
DR74 | Over- automation Without Governance | Operations | Excessive or unmanaged automation causes systemic errors and inefficiencies. | Medium | 3 | 4 | Automation inventory, process validation, exception handling | RPA/Automatio n Lead | Open
DR75 | Inconsistent Digital Brand Experience | Marketing & UX | Fragmented customer experiences across digital channels damage trust. | Medium | 3 | 4 | UX/UI guidelines, brand governance, omnichannel design | Marketing & Product Team | Open
DR76 | Digital Identity Fraud | Cybersecurit y | Fake digital identities or credentials used to access systems or services. | High | 3 | 5 | MFA, identity verification tools, fraud analytics | IAM Manager | Open
DR77 | Over- customization of Platforms | Technology | Excessive modifications reduce upgrade compatibility and increase maintenance. | Medium | 3 | 4 | Adopt standard configurations, version control policies | IT Systems Architect | Open
DR78 | Legacy System Risks | IT Infrastructure | Outdated systems create performance, security, and integration risks. | High | 4 | 4 | Modernization roadmap, isolation strategies, migration plans | Infrastructure Manager | Open
DR79 | Lack of Cyber Insurance | Financial Risk | Absence of coverage leads to heavy losses from cyber incidents. | Medium | 2 | 5 | Risk assessments, cyber insurance policy, legal advisory | CFO / Risk Manager | Open
DR80 | Incomplete Asset Discovery | IT Operations | Digital or physical assets remain undocumented, exposing blind spots. | High | 4 | 4 | Automated asset discovery tools, regular audits | ITAM Lead | Open
DR81 | Rogue IT Purchases | Shadow IT | Unapproved tools and services bypass security and budget oversight. | Medium | 4 | 3 | Procurement controls, IT policy training, discovery scans | IT Governance Officer | Open
DR82 | Algorithmic Bias | Ethical AI | AI/ML models produce unfair or discriminatory results. | Medium | 3 | 4 | Bias detection tools, diverse data sets, AI ethics reviews | AI Ethics Officer | Open
DR83 | Cross-border Data Transfer Risks | Regulatory | Transferring data between jurisdictions may violate international data laws. | High | 3 | 5 | DPA agreements, encryption-in- transit, regional data storage | Data Privacy Lead | Open
DR84 | Phishing-as-a- Service Threats | Cybercrime | Emerging dark web services make sophisticated phishing attacks accessible. | High | 3 | 5 | Threat intelligence, user awareness, advanced email filtering | SOC Analyst | Open
DR85 | SaaS Contract Expiry | Vendor Risk | SaaS subscriptions lapse unnoticed, leading to loss of service or access. | Medium | 3 | 4 | Contract calendar, renewal alerts, backup/export options | IT Vendor Manager | Open
DR86 | Over-reliance on Generative AI | Operational | Dependence on AI- generated content reduces human critical thinking and quality. | Medium | 3 | 3 | AI policy, manual review layers, skill development | Digital Content Manager | Open
DR87 | Digital Vendor Lock-in | Strategic Risk | Inability to switch platforms due to proprietary systems or costs. | Medium | 3 | 4 | Exit clauses, interoperability standards, contract flexibility | IT Strategy Lead | Open
DR88 | Lack of Quantum- readiness | Emerging Technology | Cryptographic systems may become obsolete with advances in quantum computing. | Low | 2 | 5 | Research planning, algorithm diversification, vendor engagement | CTO / Innovation Lead | Open
DR89 | Content Moderation Failure | Platform Governance | User-generated content violates laws or ethics, impacting reputation. | Medium | 3 | 4 | Moderation policies, AI moderation tools, escalation workflows | Community Manager | Open
DR90 | Lack of Digital Twin Integrity | Digital Engineering | Inaccurate virtual replicas lead to flawed simulations or decisions. | Medium | 2 | 4 | Calibration routines, validation checkpoints, audit trails | Digital Engineering Lead | Open
DR91 | Inadequate System Scalability | Architecture | Digital platforms can’t handle growing user/data volume. | High | 3 | 5 | Load testing, scalable design, cloud elasticity | Systems Architect | Open
DR92 | Poor Stakeholder Communication | Project Risk | Misalignment on goals or progress results in digital project delays. | Medium | 3 | 3 | Stakeholder matrix, communication plans, feedback loops | Project Manager | Open
DR93 | Lack of Data Literacy | Workforce & Analytics | Teams misinterpret or misuse data, affecting decisions and insights. | Medium | 4 | 3 | Data education programs, self- service BI, mentoring | L&D + Data Lead | Open
DR94 | Smart Contract Vulnerabilities | Blockchain | Flaws in smart contract logic lead to financial or legal exposure. | Medium | 2 | 5 | Auditing tools, peer review, formal verification methods | Blockchain Dev Team | Open
DR95 | Delays in Technology Adoption | Innovation | Resistance or slow rollout hinders competitiveness and digital ROI. | Medium | 3 | 4 | Change champions, pilot programs, adoption metrics | Digital Transformation Office | Open
DR96 | Overdependence on Key Tech Personnel | HR & Continuity | Loss of specialized staff disrupts continuity of critical tech systems. | High | 4 | 4 | Knowledge management, cross-training, succession plans | HRBP / IT Director | Open
DR97 | Poor Multi-Cloud Governance | Infrastructure | Uncoordinated cloud usage leads to duplication, costs, or security gaps. | Medium | 3 | 4 | Unified cloud strategy, tagging policies, central governance | Cloud Ops Team | Open
DR98 | AI Prompt Injection Attacks | AI Security | Malicious inputs manipulate generative AI behavior to produce harmful outputs. | High | 3 | 5 | Input validation, prompt filters, red teaming | AI Security Team | Open
DR99 | Inconsistent Digital Asset Valuation | Financial & Strategy | Poor understanding of digital asset worth leads to flawed investment decisions. | Medium | 2 | 4 | Asset classification model, financial tagging, audit | Digital Finance Officer | Open
DR100 | Misalignment Between IT & ESG | Sustainability | Digital operations not supporting environmental or social targets. | Medium | 2 | 5 | Green IT metrics, ESG dashboards, sustainable tech planning | ESG Officer | Open
Subramanian Shanmugam
2025-08-06
) s—) `Document Owner: Quality Excellence Management Professional Date: